## Sheet1
|  |  | Status | Work Time | Man Power | Manhour | Status | JULI
Dated
Pembuatan ECP 2102 | [7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Koneksi Feeder with bottom 1020 | Rajangan - Conditioning Line | 2A orang 1Hari | Planning | 08.00 - 17.00 | 2 |  | close | bar: Dated 1 to Dated 2; Dated 14; Dated 21; Dated 23; Dated 28
Pembuatan Panel EMC 2100 | bar: Dated 1 to Dated 2
Metering chute 1030 | Rajangan - Conditioning Line | bar: Dated 1 to Dated 2
Belt conveyor 1050 | bar: Dated 1 to Dated 2
Belt conveyor w/ metal detecting system 1080 | bar: Dated 1 to Dated 2
Two-way hopper 1090 | bar: Dated 1 to Dated 2
Realisasi
EWP 2103 |  | 2B orang 1Hari | Planning | 08.00 - 17.00 | 2 orang 1Hari | bar: Dated 1 to Dated 2
Weight belt conveyor 1040 | Rajangan - Conditioning Line | bar: Dated 1 to Dated 2
Realisasi
ECP 2104
Conditioning Cylinder 1060 | Rajangan - Conditioning Line | 2A orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 1 to Dated 2
Realisasi
ESP 2104.1
Service cubicle (New) 1061 | Rajangan - Conditioning Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari | bar: Dated 3 to Dated 4
ESSP 2100-A1 | bar: Dated 3 to Dated 4
Vibratory conveyor 1070 | Rajangan - Conditioning Line | bar: Dated 3 to Dated 4
ESP 2100.1 | bar: Dated 3 to Dated 4
Troughed belt conveyor 1100 | Rajangan - Conditioning Line | bar: Dated 3 to Dated 4
Reversible belt conveyor 1110 | Rajangan - Conditioning Line | bar: Dated 3 to Dated 4
Troughed belt conveyor 1240 | Rajangan - Conditioning Line | bar: Dated 3 to Dated 4
Realisasi
ESSP 2100.1-A1
Vibratory conveyor 1250 | Rajangan - Conditioning Line | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 3 to Dated 4
ECP 2107 | [5 empty] | Manhour | Status | bar: Dated 3 to Dated 4
Separating disk conveyor 1260 | Rajangan - Conditioning Line | bar: Dated 3 to Dated 4
Inching conveyor 1270 | Rajangan - Conditioning Line | bar: Dated 3 to Dated 4
|  |  | Realisasi |  |  |  | close
ESP 2100.3
Troughed belt conveyor 1280 | Rajangan - Conditioning Line | 2A orang 1 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari | bar: Dated 3
Troughed belt conveyor 1320 | bar: Dated 3
EWP 2108 | bar: Dated 3
Weight belt conveyor 1290 | Rajangan - Conditioning Line | bar: Dated 3
Realisasi
ESSP 2100.3-A1
Vibratory conveyor 1300 | Rajangan - Conditioning Line | 2A orang 1 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari | bar: Dated 4
ECP 2110 | bar: Dated 4
Thresher 1310 | Rajangan - Conditioning Line | bar: Dated 4
EWP 2109 | bar: Dated 4
Weight belt conveyor 1330 | Rajangan - Conditioning Line | bar: Dated 4
Realisasi
ESSP 2100.3-A2
Vibratory conveyor 1340 | Rajangan - Conditioning Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 5 to Dated 6
ESSP 2111-A1 | bar: Dated 5 to Dated 6
Rotary Airlock 1350 | Rajangan - Conditioning Line | bar: Dated 5 to Dated 6
ECP 2111 | bar: Dated 5 to Dated 6
Air Product Separator 1360 | Rajangan - Conditioning Line | bar: Dated 5 to Dated 6
Air Product Separator 1360 | Rajangan - Conditioning Line | bar: Dated 5 to Dated 6
Rotary airlock 1361 | Rajangan - Conditioning Line | bar: Dated 5 to Dated 6
Centrifugal Fan 1362 | Rajangan - Conditioning Line | bar: Dated 5 to Dated 6
Realisasi
ECP 2112
Classifiying Chamber 1370 | Rajangan - Conditioning Line | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | Manhour | Status | bar: Dated 5 to Dated 6
Mesh belt conveyor 1371 | Rajangan - Conditioning Line | bar: Dated 5 to Dated 6
Rotary airlock 1372 | Rajangan - Conditioning Line | bar: Dated 5 to Dated 6
Airknife system 1373 | Rajangan - Loosening Line | [5 empty] | close | bar: Dated 5 to Dated 6
Air Product Separator 1380 | Rajangan - Loosening Line | bar: Dated 5 to Dated 6
Rotary airlock 1381 | Rajangan - Loosening Line | bar: Dated 5 to Dated 6
Centrifugal Fan 1382 | Rajangan - Loosening Line | bar: Dated 5 to Dated 6
Realisasi
EWP 2123
Weight belt conveyor 1390 | Rajangan - Loosening Line | 2A orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 5 to Dated 6
ECP 2113 | bar: Dated 5 to Dated 6
Thresher 1400 | Rajangan - Loosening Line | bar: Dated 5 to Dated 6
ECP 2114 | bar: Dated 5 to Dated 6
Air Product Separator 1410 | Rajangan - Loosening Line | bar: Dated 5 to Dated 6
Rotary airlock 1411 | Rajangan - Loosening Line | bar: Dated 5 to Dated 6
Centrifugal Fan 1412 | Rajangan - Loosening Line | bar: Dated 5 to Dated 6
Realisasi
ECP 2115
Classifiying Chamber 1420 | Rajangan - Loosening Line | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 7 to Dated 8
Mesh belt conveyor 1421 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Rotary airlock 1422 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Airknife system 1423 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Air Product Separator 1430 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Rotary airlock 1431 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Centrifugal Fan 1432 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Realisasi
EWP 2124
Weight belt conveyor 1440 | Rajangan - Loosening Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 7 to Dated 8
ECP 2116 | [5 empty] | Manhour | Status | bar: Dated 7 to Dated 8
Air Product Separator 1450 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Rotary airlock 1451 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Centrifugal Fan 1452 | Rajangan - Loosening Line | [5 empty] | close | bar: Dated 7 to Dated 8
Realisasi
ESSP 2118-A1
Heavy Particle Separator 1460 | Rajangan - Loosening Line | 2A orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari | bar: Dated 7 to Dated 8
ECP 2117 | bar: Dated 7 to Dated 8
Hammermill 1470 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
ECP 2118 | bar: Dated 7 to Dated 8
Air Product Separator 1480 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Rotary airlock 1481 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Centrifugal Fan 1482 | Rajangan - Loosening Line | bar: Dated 7 to Dated 8
Realisasi | bar: Dated 7 to Dated 8
ECP 2119
Classifiying Chamber 1490 | Rajangan - Loosening Line | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 9 to Dated 10
Mesh belt conveyor 1491 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Rotary airlock 1492 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Airknife system 1493 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Air Product Separator 1500 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Rotary airlock 1501 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Centrifugal Fan 1502 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Realisasi
ESMC 2140
Belt conveyor 1510 | Rajangan - Loosening Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 9 to Dated 10
ECP 2120 | bar: Dated 9 to Dated 10
Air Product Separator 1520 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Rotary airlock 1521 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Centrifugal Fan 1522 | Rajangan - Loosening Line |  |  |  |  | Manhour | Status | bar: Dated 9 to Dated 10
ECP 2122 | bar: Dated 9 to Dated 10
Hammer mill 1530 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
|  |  | Realisasi |  |  |  | close
ECP 2121
Air Product Separator 1540 | Rajangan - Loosening Line | 2A orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 9 to Dated 10
Rotary airlock 1541 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Centrifugal Fan 1542 | Rajangan - Loosening Line | bar: Dated 9 to Dated 10
Realisasi
ECP 2134 |  | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 11 to Dated 12
Cyclone 1550 | Rajangan - Loosening Line | bar: Dated 11 to Dated 12
Centrifugal Fan 1551 | Rajangan - Loosening Line | bar: Dated 11 to Dated 12
Realisasi
ESP 2100.4
Troughed belt conveyor 1560 | Rajangan - Loosening Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 11 to Dated 12
EWP 2125 | bar: Dated 11 to Dated 12
Weight belt conveyor 1565 | Rajangan - Loosening Line | bar: Dated 11 to Dated 12
ESP 2100.4 | bar: Dated 11 to Dated 12
Troughed belt conveyor 1570 | Rajangan - Loosening Line | bar: Dated 11 to Dated 12
Troughed belt conveyor 1580 | Rajangan - Loosening Line | bar: Dated 11 to Dated 12
Realisasi
ECP 2126
Inching conveyor 1590 | Rajangan - Loosening Line | 2A orang 4 hari | Planning | 08.00 - 17.00 | 2 orang 4 hari | bar: Dated 11 to Dated 14
ECP 2127 | bar: Dated 11 to Dated 14
Mini silo 1600 | Rajangan - Loosening Line | bar: Dated 11 to Dated 14
Realisasi
ESP 2100.5 | bar: Dated 13 to Dated 14
Metering chute 1610 | Rajangan - Loosening Line | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 13 to Dated 14
Troughed belt conveyor 1630 | [5 empty] | Manhour | Status | bar: Dated 13 to Dated 14
EWP 2128 | bar: Dated 13 to Dated 14
Weight belt conveyor 1620 | Rajangan - Loosening Line | bar: Dated 13 to Dated 14
ECP 2129 | [6 empty] | close | bar: Dated 13 to Dated 14
Casing cylinder 1640 | Rajangan - Loosening Line | bar: Dated 13 to Dated 14
Realisasi
ESP 2129.1
Service cubicle (New) 1641 | Rajangan - Loosening Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 13 to Dated 14
ECP 2130 | bar: Dated 13 to Dated 14
Casing tank 1642 | Rajangan - Loosening Line | bar: Dated 13 to Dated 14
Casing Pump 1643 | Rajangan - Loosening Line | bar: Dated 13 to Dated 14
Casing tank 1644 | Rajangan - Loosening Line | bar: Dated 13 to Dated 14
Casing Pump 1645 | Rajangan - Loosening Line | bar: Dated 13 to Dated 14
Casing tank 1646 | Rajangan - Loosening Line | bar: Dated 13 to Dated 14
Casing Pump 1647 | Rajangan - Loosening Line | bar: Dated 13 to Dated 14
Realisasi
ESP 2100.6
Troughed belt conveyor 1650 | Rajangan - Loosening Line | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 15 to Dated 16
Troughed belt conveyor 1660 | Rajangan - Loosening Line | bar: Dated 15 to Dated 16
ECP 2201 | bar: Dated 15 to Dated 16
Feeder with bottom 2020 | Rajangan - Loosening Line | bar: Dated 15 to Dated 16
EMC 2200 | bar: Dated 15 to Dated 16
Metering chute 2030 | Rajangan - Loosening Line | bar: Dated 15 to Dated 16
Troughed belt conveyor 2050 | bar: Dated 15 to Dated 16
Belt conveyor w/ metal detecting system 2090 | bar: Dated 15 to Dated 16
Two-way hopper 2100 | bar: Dated 15 to Dated 16
Troughed belt conveyor 2110 | bar: Dated 15 to Dated 16
Realisasi
EWP 2202 | [5 empty] | Manhour | Status
Weight belt conveyor 2040 | Rajangan - Loosening Line | 2A orang 4 hari | Planning | 08.00 - 17.00 | 2 orang 4 hari | bar: Dated 15 to Dated 18
ECP 2204 | bar: Dated 15 to Dated 18
Conditioning & Casing Cylinder 2060 | Rajangan - Loosening Line | [5 empty] | close | bar: Dated 15 to Dated 18
ESP 2204.1 | bar: Dated 15 to Dated 18
Service cubicle (New) 2061 | Rajangan - Loosening Line | bar: Dated 15 to Dated 18
Realisasi
ECP 2205 | bar: Dated 15 to Dated 16
Casing tank 2070 | Rajangan - Loosening Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari | bar: Dated 15 to Dated 16
Casing Pump 2075 | Rajangan - Loosening Line | bar: Dated 15 to Dated 16
ESSP 2200-A1 | bar: Dated 15 to Dated 16
Vibratory conveyor 2080 | Rajangan - Loosening Line | bar: Dated 15 to Dated 16
Realisasi
ECP 2206 |  | 2B & 2C 4 orang 6hari | Planning | 08.00 - 17.00 | 4 orang 4hari | bar: Dated 17 to Dated 22
Troughed belt conveyor 2120 | Krosok Line | bar: Dated 17 to Dated 22
Stepping conveyor 2130 | Krosok Line | bar: Dated 17 to Dated 22
ECP 2207 | bar: Dated 17 to Dated 22
Blending conveyor 2140 | Krosok Line | bar: Dated 17 to Dated 22
Blending carrier 2141 | Krosok Line | bar: Dated 17 to Dated 22
ECP 2301 | bar: Dated 17 to Dated 22
Silo blending 2150 | Krosok Line | bar: Dated 17 to Dated 22
ECP 2302 | bar: Dated 17 to Dated 22
Silo blending 2155 | Krosok Line | bar: Dated 17 to Dated 22
Realisasi
EMC 2300
Troughed belt conveyor 2160 | Krosok Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari | bar: Dated 19 to Dated 20
Troughed belt conveyor 2165 | Krosok Line | bar: Dated 19 to Dated 20
Troughed belt conveyor 2170 | Krosok Line | bar: Dated 19 to Dated 20
Metering chute 2180 | Krosok Line |  |  |  |  | Manhour | Status | bar: Dated 19 to Dated 20
Troughed belt conveyor 2215 | bar: Dated 19 to Dated 20
Troughed belt conveyor 2250 | bar: Dated 19 to Dated 20
Troughed belt conveyor 2260 | [6 empty] | close | bar: Dated 19 to Dated 20
Troughed belt conveyor 2270 | bar: Dated 19 to Dated 20
Realisasi
EWP 2303
Weight belt conveyor 2190 | Krosok Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari | bar: Dated 23 to Dated 24
ECP 2304 | bar: Dated 23 to Dated 24
Separating disk conveyor 2200 | Krosok Line | bar: Dated 23 to Dated 24
Belt conveyor 2205 | Krosok Line | bar: Dated 23 to Dated 24
Realisasi
ESSP 2300-A1
Vibratory conveyor w/sieving system 2210 | Krosok Line | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 23 to Dated 24
Vibratory conveyor 2220 | Krosok Line | bar: Dated 23 to Dated 24
Tobacco cutter 2230 | Krosok Line | bar: Dated 23 to Dated 24
Vibratory conveyor 2240 | Krosok Line | bar: Dated 23 to Dated 24
Realisasi
ECP 2131
Troughed belt conveyor 3010 | Krosok Line | 2B & 2C 4 orang 6 hari | Planning | 08.00 - 17.00 | 4 orang 4 hari | bar: Dated 25 to Dated 30
Stepping conveyor 3020 | Krosok Line | bar: Dated 25 to Dated 30
ECP 2132 | bar: Dated 25 to Dated 30
Blending conveyor 3030 | Krosok Line | bar: Dated 25 to Dated 30
Blending carrier 3031 | Krosok Line | bar: Dated 25 to Dated 30
ECP 2401 | bar: Dated 25 to Dated 30
Silo blending 3040 | Krosok Line | bar: Dated 25 to Dated 30
ECP 2133 | bar: Dated 25 to Dated 30
Blending conveyor 3050 | Krosok Line |  |  |  |  | Manhour | Status | bar: Dated 25 to Dated 30
Blending carrier 3051 | Drying Line | bar: Dated 25 to Dated 30
ECP 2402 | bar: Dated 25 to Dated 30
Silo blending 3060 | Drying Line | [5 empty] | close | bar: Dated 25 to Dated 30
Realisasi
ESP 2400.1
Troughed belt conveyor 3070 | Drying Line | 2A Orang 2 hari | Planning | 08.00 - 17.00 | 2 Orang 1 hari | bar: Dated 21 to Dated 22
Troughed belt conveyor 3080 | Drying Line | bar: Dated 21 to Dated 22
Troughed belt conveyor 3200 | bar: Dated 21 to Dated 22
Troughed belt conveyor 3210 | bar: Dated 21 to Dated 22
ESP 2400.2 | bar: Dated 21 to Dated 22
Troughed belt conveyor 3090 | Drying Line | bar: Dated 21 to Dated 22
Troughed belt conveyor 3100 | Drying Line | bar: Dated 21 to Dated 22
Metering chute 3130 | bar: Dated 21 to Dated 22
Troughed belt conveyor 3150 | bar: Dated 21 to Dated 22
ECP 2403 |  |  | Realisasi
Inching conveyor 3110 | Drying Line | 2A Orang 2 hari | Planning | 08.00 - 17.00 | 2 Orang 2 hari | bar: Dated 23 to Dated 24
ECP 2404 | bar: Dated 23 to Dated 24
Mini silo 3120 | Drying Line | bar: Dated 23 to Dated 24
EWP 2405 | bar: Dated 23 to Dated 24
Weight belt conveyor 3140 | Drying Line | bar: Dated 23 to Dated 24
ECP 2406 |  |  | Realisasi
Vibratory conveyor 3160 | Drying Line
Drying cylinder 3170 | Drying Line | Done
ECP 2420
Cyclone 3180 | Drying Line
Centrifugal fan 3190 | Drying Line
ZS3230
Vibratory conveyor 3220 | Drying Line |  |  |  |  | Manhour | Status
Vluidized bed separator 3230 | Drying Line
Separator 3240 | Drying Line
ZK3230.2 | [6 empty] | close
Belt conveyor 3250 | Drying Line
Vibratory conveyor 3260 | Drying Line
Small conveyor 3270 | Drying Line
Small conveyor 3280 | Drying Line
Vibratory feeder 3290 | Drying Line
Zig-zag separator 3300 | Drying Line
ECP 2421
Cyclone 3320 | Drying Line
Centrifugal fan 3330 | Drying Line
ESP 2400.3
Troughed belt conveyor 3340 | Drying Line | 2A orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari | bar: Dated 25 to Dated 26
Troughed belt conveyor 4090 | bar: Dated 25 to Dated 26
EWP 3350 | bar: Dated 25 to Dated 26
Weight belt conveyor 3350 | Drying Line | bar: Dated 25 to Dated 26
ECP 2409 |  |  | Realisasi
Lift and tipper 4010 | Drying Line | 2A orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 27 to Dated 28
ECP 2410 | bar: Dated 27 to Dated 28
Feeder 4020 | Drying Line | bar: Dated 27 to Dated 28
EMC 2400 | bar: Dated 27 to Dated 28
Metering chute 4021 | Drying Line | bar: Dated 27 to Dated 28
Multiple screw conveyor 4050 | bar: Dated 27 to Dated 28
Troughed belt conveyor 4080 | bar: Dated 27 to Dated 28
Troughed belt conveyor 4100 | bar: Dated 27 to Dated 28
Troughed belt conveyor 4150 | Final Blend Line | bar: Dated 27 to Dated 28
EWP 2411 |  |  | Realisasi |  |  | Manhour | Status
Weight belt conveyor 4030 | Drying Line | 2A orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 29 to Dated 30
ECP 2412 | bar: Dated 29 to Dated 30
Lift and tipper 4040 | Drying Line | [5 empty] | close | bar: Dated 29 to Dated 30
EWP 2413 | bar: Dated 29 to Dated 30
Weight belt conveyor 4060 | Drying Line | bar: Dated 29 to Dated 30
ESP 2400.4 |  |  | Realisasi
Reversible Throughed belt conveyor 4070 | Drying Line | 2A orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari | bar: Dated 31
ECP 2414 | bar: Dated 31
Top flavouring cylinder 4110 | Drying Line | bar: Dated 31
-Exhaust fan 4110 | Drying Line | bar: Dated 31
ESP 2414.1 | bar: Dated 31
Service cubicle (New) 4120 | Final Blend Line | bar: Dated 31
ECP 2415 | bar: Dated 31
Flavour tank 4130 | Final Blend Line | bar: Dated 31
Flavour Pump 4135 | Final Blend Line
EWP 2416 |  |  | Realisasi
Weight belt conveyor 4160 | Final Blend Line | 2A orang 2 Hari | Planning | 08.00 - 17.00 | 2 orang 1 Hari | bar: Dated 31
ECP 2417 | bar: Dated 31
Troughed belt conveyor 4170 | Final Blend Line | bar: Dated 31
Stepping conveyor 4180 | Final Blend Line |  | Realisasi | bar: Dated 31
ECP 2418 |  | 2b & 2C 4 orang 6 hari | Planning | 08.00 - 17.00 | 4 orang 6 hari
Blending conveyor 4190 | Final Blend Line
Blending carrier 4191 | Final Blend Line
ECP 2501
Silo blending 4200 | Final Blend Line
ECP 2419
Blending conveyor 4210 | Final Blend Line
Blending carrier 4211 | Final Blend Line |  |  |  |  | Manhour | Status
ECP 2502
Silo blending 4220 | Final Blend Line
EMC 2500 |  |  | Realisasi |  |  |  | close
Troughed belt conveyor 4250 | Final Blend Line | 2C orang 1 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari
Belt conveyor w/ metal detecting system 4260 | Final Blend Line
Two-way hopper 4270 | Final Blend Line
Troughed belt conveyor 4280 | Final Blend Line
Troughed belt conveyor 4310
Metering chute 4320
ECP 2503 |  | 2A orang 2 hari | Realisasi | 08.00 - 17.00 | 2 orang 2 hari
Inching conveyor 4290 | Final Blend Line |  | Planning
ECP 2504
Mini silo 4300 | Final Blend Line
EWP 2505 |  |  | Realisasi
Weight belt conveyor 4330 | Final Blend Line | 2A orang 1 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari
ESMC 2530
Troughed belt conveyor 4340 | Final Blend Line
ESSP 2500.2-A1
Vibratory conveyor 4350 | Final Blend Line
Vibratory conveyor 4350 | Bin Filling Line
ECP 2506 |  |  | Realisasi
Inching conveyor 4360 | Bin Filling Line | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari
ECP 2507
Pressed unit 4370 | Bin Filling Line
Feeding Hopper 4381
ECP 2508 |  |  | Realisasi
Pressed unit 4380 | Bin Filling Line | 2A orang 1 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari
Bin de-stacker unit 4430 | [5 empty] | Manhour | Status
Chain conveyor w/weighing system 4490
ESP 2500.1 |  |  | Realisasi
Roller conveyor 4400 | Bin Filling Line | 2A orang 1 hari | Planning | 08.00 - 17.00 | 2 orang 1 hari |  | close
Roller conveyor 4410 | Bin Filling Line
Roller conveyor 4420 | Bin Filling Line
Roller conveyor 4450
Chain conveyor 4470
ESP 2500.2
Roller - Chain conveyor 4440 | Bin Filling Line
Chain conveyor 4480
Roller - Chain conveyor 4500
ESP 2500.3 |  |  | Realisasi
Roller - Chain conveyor 4460 | Bin Filling Line | 2C orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari
Chain conveyor 4510 | Bin Filling Line
Roller - Chain conveyor 4530
ECP 2507
Chain conveyor w/weighing system 4520 | Bin Filling Line
ESP 2500.4
Roller conveyor 4540 | Bin Filling Line
Roller conveyor 4550 | Bin Filling Line
Roller conveyor 4560 | Bin Filling Line
Roller conveyor 4580
ECP 2509 |  |  | Realisasi
Bin stacker unit 4570 | Bin Filling Line | 2B orang 2 hari | Planning | 08.00 - 17.00 | 2 orang 2 hari
ESP 2500.5
Toothed Belt Conveyor 4590 | Bin Filling Line
Toothed Belt Conveyor 4600 | Bin Filling Line
Lid pick-up robotic 4610 | Bin Filling Line
Realisasi